## Test Plan
Please click here for FlightExpert testplan full PDF.

## Mind Maps
Mind Map of Flight Expert Web Application

## TestScenarios
Project Name | Flight Expert
Reference Document | FRS
Created By | Md Jahidul Islam
Creation Date | 2025-03-12
Approval Date
Test Scenario ID | Reference | Test Scenario Description | Priority | Number of Test Cases
TS_001 |  | Verify that users can create an account using email and phone number. | P0
TS_002 |  | Verify that users receive an OTP for verification | P0
TS_003 |  | Verify that login works correctly with valid credentials. | P0
TS_004 |  | Verify that incorrect login attempts show appropriate error messages. | P1
TS_005 |  | Verify that users can reset their password via email. | P0
TS_006 |  | Verify that clicking logout logs the user out and redirects to the home page. | P0
TS_007 |  | Verify that users can update their profile details. | P3
TS_008 |  | Verify that users can view past bookings in Dashboard | P3
TS_010 |  | Verify that flight search & filters work properly | P0
TS_011 |  | Verify that users can select a flight and proceed to booking. | P0
TS_012 |  | Verify that passenger details (name, passport number, DOB) can be entered. | P0
TS_013 |  | Verify that users can proceed to payment successfully. | P0
TS_014 |  | Verify that users receive a confirmation email with ticket details after booking. | P1
TS_015 |  | Verify that users can download their e-ticket from their account. | P1
TS_016 |  | Verify that users can change flight details | P2
TS_017 |  | Verify that users can modify/cancel Flight bookings as per policy. | P2
TS_018 |  | Verify that Hotels search & filters work properly | P0
TS_019 |  | Verify that users can choose a room and proceed with the booking. | P0
TS_020 |  | Verify that payment is processed correctly. | P0
TS_021 |  | Verify that users receive booking confirmation via email. | P1
TS_022 |  | Verify that users can modify/cancel hotel bookings as per policy. | P2
TS_023 |  | Verify that users can search for visa processing services by country. | P0
TS_024 |  | Verify that users can upload required documents successfully. | P0
TS_025 |  | Verify that users can track visa application status. | P0
TS_026 |  | Verify that users can search for eSIMs by country. | P0
TS_027 |  | Verify that users can browse available eSIM plans. | P0
TS_028 |  | Verify that users can successfully make a payment. | P0
TS_029 |  | Verify that users receive a code for activation after purchase | P0
TS_030 |  | Verify that users can make payments using different methods (Credit Card, Mobile Banking). | P4
TS_031 |  | Verify that payment failure cases show appropriate error messages. | P4
TS_032 |  | Verify that discount codes apply correctly. | P1
TS_033 |  | Verify that the Contact Us number or mail is working. | P3
TS_034 |  | Verify that FAQs load correctly and provide helpful information. | P4

## TestCase
Product Name |  | Flight Expert | TC Start Date | 2025-12-01 | TC Execution Start Date | - - | [5 empty] | TEST CASE
Module Name |  | Account | TC End Date | 15/1/2025 | TC Execution End Date | - - |  |  |  |  | PASS | 1
Epic |  |  | Test Case Developed By | Md Jahidul Islam | Browser (tested) | Yes |  |  |  |  | FAIL | 0
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | NO RUN | 82
Test Executed by | [10 empty] | BLOCKED | 0
[11 empty] | TOTAL | 83
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bugs Screen Shot | Dev Comments | Final Status | Remarks
1 | Account | Browser Compatibility Testing | Account | Checkinging by running the URL site in different browsers. | Should be run in different browsers. | Found as per expectation. | Browsers-Chrome, Internet Explorer, Mozilla Firefox, Microsoft Edge, Opera Mini. | 1. Go to different browsers. 2. Search for ' https://flightexpert.com/ ' 3. Ckeck Website. |  |  | Passed
2 | User Authentication |  | Login | Verifying that the user will be able to log in with their account with the correct credential. | User should be able to login with correct credintial | Found as per expectation. |  | 1. Go to the URL " https://flightexpert.com/" 2. Click on Sign in button 3. Enter correct credentials 4. Click on Sign in button |  |  | Not Executed
3 |  |  |  | Verifying all login-related elements and fields are present on the login page. | Should be present the all mandatory field | Found as per expectation. |  | 1. Go to the URL " https://flightexpert.com/" |  |  | Not Executed
4 |  |  |  | Verifying that the user will get into their dashboard screen after login in with the correct credentials. | User should be redirected to the dashboard after successful login. | Found as per expectation. |  |  |  |  | Not Executed
5 |  |  |  | Verifying that the user can log in by entering valid credentials and presseing "Enter" key. | Should be able to log in successfully | Found as per expectation. |  |  |  |  | Not Executed
6 |  |  |  | Verifying that the user can log in by entering valid credentials and presseing "Login" button. | Should be able to log in successfully | Found as per expectation. |  |  |  |  | Not Executed
7 |  |  |  | Verifying that the password entered should be in encrypted form. | The password should be displayed in encrypted form while being entered. | Found as per expectation. |  |  |  |  | Not Executed
8 |  |  |  | Verifying whether an eye icon is added to the password field or not. | Eye-icon should be added to the password | Not found as per expectation. |  |  |  |  | Not Executed
9 |  |  |  | Verifying the error message should display after just entering an email and leaving the password field blank. | An error message should be displayed after entering an email and leaving the password field blank. | Found as per expectation. |  |  |  |  | Not Executed
10 |  |  |  | Verifying the error message should display after just entering the passowrd and leaving the email field blank. | An error message should be displayed after entering a password and leaving the email field blank. | Found as per expectation. |  |  |  |  | Not Executed
11 |  |  |  | Verifying that error message should display after entering the invalid credentials. | The error message should display after just entering invalid credentials | Found as per expectation. |  |  |  |  | Not Executed
12 |  |  |  | Verifying that error message should display after entering an invalid email format. | The error message should display after entering an invalid email format | Found as per expectation. |  |  |  |  | Not Executed
13 |  |  |  | Verifying logged-in user doesn’t log out by clicking the back button on the browser tab. | User should not logged out by clicking the back button on the browser tab | Found as per expectation. |  |  |  |  | Not Executed
14 |  |  |  | Verifying the displayed error message grammar should be correct. | The error message should be grammatically correct. | Found as per expectation. |  |  |  |  | Not Executed
15 |  |  |  | Verifying the displayed error message spell should be correct. | The spelling of error message should be correct. | Found as per expectation. |  |  |  |  | Not Executed
16 |  |  |  | Checking logged in user should not log out on closing the browser. | Browser should not be closed when new browser is openned | Found as per expectation. |  |  |  |  | Not Executed
17 |  |  |  | Verifying the login session timeout duration. So, once logged in a user cannot be authenticated for a lifetime. | The login session should time out after a specified duration, requiring the user to log in again for continued access. | Found as per expectation. |  |  |  |  | Not Executed
18 |  |  |  | Verifying that there is a limit to the total number of unsuccessful login attempts. | The system should limit unsuccessful login attempts and show an error message after the limit is reached. | Found as per expectation. |  |  |  |  | Not Executed
19 |  |  |  | Verifying the login screen will appear after clicking on a login link or login button. | The login screen should appear after clicking the login link or button. | Found as per expectation. |  |  |  |  | Not Executed
20 |  |  |  | Verifying that the login page of the application is responsive and aligns properly on different screen resolutions and devices. | The login page should be responsive and properly aligned on different screen resolutions and devices. | Found as per expectation. |  |  |  |  | Not Executed
21 |  |  |  | Verifying login page title. | The login page should display the correct title as per the application’s specifications. | Found as per expectation. |  |  |  |  | Not Executed
22 |  |  |  | Verifying if keyboard shortcut keys enable in the text area. Users can copy, cut or paste and select content on shift + Arrow Keys. | Keyboard shortcuts (copy, cut, paste, Shift + Arrow) should work in the text area. | Found as per expectation. |  |  |  |  | Not Executed
23 |  |  |  | Verifying that the text area is functional in case of any validation error message shown. | The text area should be functional during validation errors. | Found as per expectation. |  |  |  |  | Not Executed
24 |  |  |  | Verifying Backspace, delete keys should be functional | Backspace and Delete keys should be functional in the text area. | Found as per expectation |  |  |  |  | Not Executed
25 |  |  |  | Verifying user can paste the copied content with keyboard keys Ctrl + v. | User should be able to paste copied content using Ctrl + V. | Functioning successfully |  |  |  |  | Not Executed
26 |  |  |  | Verifying the input text area is protected from the SQL injection. | The input text area should be protected from SQL injection attacks. | Functioning successfully |  |  |  |  | Not Executed
27 |  |  |  | Verifying user can type in the text area after clicking in the text area. | User should be able to type in the text area after clicking on it. | Found as per expectation |  |  |  |  | Not Executed
28 |  |  |  | After the user login page is open, the curson should remain in the username text box by default. | After the login page is opened, the cursor should remain in the username text box by default. | Not found as per expectation. |  |  |  |  | Not Executed
29 |  |  | Logout | Verify Successful Logout | User should be logged out successfully and redirected to the login page | Found as per expectation. |  |  |  |  | Not Executed
30 |  |  |  | Verify Logout Button Visibility | The "Logout" button should be clearly visible and accessible. | Found as per expectation. |  |  |  |  | Not Executed
31 |  |  |  | Verify Logout from Multiple Devices | Only the logged-out device's session should end. | Found as per expectation. |  |  |  |  | Not Executed
32 | User Registration |  | Register Account | Verifying by clicking on the "Register" button for blank input. | Clicking the "Register" button with blank input should show an error message. | Found as per expectation. |  |  |  |  | Not Executed
33 |  |  |  | Verifying all fields related to registration present on the registration form. | All required fields should be present on the registration form. | Found as per expectation. |  |  |  |  | Not Executed
34 |  |  |  | Verifying password field should have validation for a minimum of 5 characters long. | Password field should validate at least 5 characters. | Found as per expectation. |  |  |  |  | Not Executed
35 |  |  |  | Verifying password added by the user should be protected, encrypted, and shown in (...). | The password should be encrypted and displayed as dots (…). | Found as per expectation |  |  |  |  | Not Executed
36 |  |  |  | Verifying whether the validation is added for the password and confirm whether passwords are the same or not. | Password validation should be applied, and the system should confirm if the passwords match. | Found as per expectation |  |  |  |  | Not Executed
37 |  |  |  | Verifying an eye icon added to the password and confirm the password field. | An eye icon should be present to toggle password visibility. | Not found as per expectation |  |  |  |  | Not Executed
38 |  |  |  | Verifying that validation is added to the email field, only valid emails should be allowed to register successfully. | The email field should validate that only valid emails can be registered. | Found as per expectation |  |  |  |  | Not Executed
39 |  |  |  | Verifying that the user adds blank spaces and clicks on the register button an error message should be shown. | An error message should be shown. | Found as per expectation |  |  |  |  | Not Executed
40 |  |  |  | Verifying users can register successfully by entering valid credentials. | Users should be able to register successfully with valid credentials. | Found as per expectation |  |  |  |  | Not Executed
41 |  |  |  | Verifying that the user is not allowed to register an account with the same registered email by adding plus for example useractual+1@gmail.com. | Should not be able to register | Found as per expectation. |  |  |  |  | Not Executed
42 |  |  |  | Test by trying to register with an already registered email address | Should not be able to register | Found as per expectation. |  |  |  |  | Not Executed
43 |  |  |  | Verifying the email verification link was sent to the user's email address successfully. | The email verification link should be sent to the user's email successfully. | Not found as per expectation |  |  |  |  | Not Executed
44 |  |  |  | Verifying the user is informed to check the spam folder if no email link is found in the inbox. | Should be informed to check the spam folder if the email link is not found in the inbox. | Not found as per expectation |  |  |  |  | Not Executed
45 |  |  |  | Verifying Resend Link option is present if the user did not receive the link in the email. | A "Resend Link" option should be available if the user did not receive the email link. | Not found as per expectation |  |  |  |  | Not Executed
46 |  |  |  | Verifying all spelling mistakes on the Register page. | Spelling should be correct. | Found as per expectation |  |  |  |  | Not Executed
47 | Transaction Processing |  | Transaction Functionality | Verifying successful transaction with valid payment details | Transaction should be processed successfully with a confirmation message | Found as per expectation |  |  |  |  | Not Executed
48 |  |  |  | Verifying transaction failure with invalid payment details. | Transaction should fail, and an error message should be displayed. | Found as per expectation |  |  |  |  | Not Executed
49 |  |  |  | Verifying transaction with insufficient funds. | Transaction should be declined due to insufficient funds, with an appropriate error message | Found as per expectation |  |  |  |  | Not Executed
50 |  |  |  | Verifying transaction details are recorded correctly in the transaction history | Transaction details (amount, date, payment method) should appear accurately in the user's transaction history. | Found as per expectation |  |  |  |  | Not Executed
51 |  |  |  | Verifying correct transaction amount is charged. | The charged amount should match the transaction amount. | Found as per expectation |  |  |  |  | Not Executed
52 |  |  |  | Verifying user is notified upon successful transaction completion. | User should receive a notification (email/SMS) upon successful transaction. | Not found as per expectation |  |  |  |  | Not Executed
53 | Inquiry Handling |  | Contact Us Functionality | Verifying user can initiate a "Contact Us" request via Facebook | Should able to send a direct message | Found as per expectation |  |  |  |  | Not Executed
54 |  |  |  | Verifying user can initiate a "Contact Us" request via Twitter. | Should able to send a direct message | Found as per expectation |  |  |  |  | Not Executed
55 |  |  |  | Verifying user can initiate a "Contact Us" request via LinkedI | Should able to send a direct message | Found as per expectation |  |  |  |  | Not Executed
56 |  |  |  | Verifying if the "Contact us" link work properly | link Should redirect user to correct page | Found as per expectation |  |  |  |  | Not Executed
57 |  |  |  | Verifying that the "Contact Us" functionality works across different devices (desktop, mobile) when using Facebook, Twitter, or LinkedIn | Should work seamlessly across various devices | Found as per expectation |  |  |  |  | Not Executed
58 | Password Reset |  | Forget password | Verifying that forget password link should be present on the login screen | Forgot Password" link should be visible and clickable on the login screen. | Found as per expectation |  |  |  |  | Not Executed
59 |  |  |  | Verifying that on clicking on the forget password link forget password page should open. | Clicking "Forgot Password" should open the password recovery page. | Found as per expectation |  |  |  |  | Not Executed
60 |  |  |  | Verifying that the email field is present on the forget password page to recover the password. | Email field should be present on the "Forgot Password" page. | Found as per expectation |  |  |  |  | Not Executed
61 |  |  |  | Verifying as the user update password, the user should log out from all browser and devices. | Updating the password should log the user out from all browsers and devices. | Not found as per expectation |  |  |  |  | Not Executed
62 |  |  |  | Verifying Submit button should be present on the page. | Submit button should be present on the page. | Found as per expectation |  |  |  |  | Not Executed
63 |  |  |  | Verifying the whole button should be clickable not only the button text. | The entire button, not just the text, should be clickable. | Found as per expectation |  |  |  |  | Not Executed
64 |  |  |  | Verifying the displayed error message for unregistered should be meaningful. | Error message for unregistered users should be clear and informative. | Found as per expectation |  |  |  |  | Not Executed
65 |  |  |  | Verifying the confirmation message check your email to recover the password should be displayed after clicking on the button by entering the registered email id. | A confirmation message should appear to check the email for password recovery. | Found as per expectation |  |  |  |  | Not Executed
66 |  |  |  | Verifying that the user will get an email after entering a valid email id in forget password. | User should receive an email after entering a valid email ID in "Forgot Password." | Not found as per expectation |  |  |  |  | Not Executed
67 |  |  |  | Verifying the email which the user gets against forgot password should be displayed in the inbox, not in the spam folder. | The password recovery email should appear in the inbox, not the spam folder. | Not found as per expectation |  |  |  |  | Not Executed
68 |  |  |  | Verifying the user will get the forget password email from info@sitename.com. | The password recovery email should be sent from info@sitename.com. | Not found as per expectation |  |  |  |  | Not Executed
69 |  |  |  | Verifying the heading displayed in forget password screen should be ” Forget Password “ | The heading should be "Forgot Password." | Not found as per expectation |  |  |  |  | Not Executed
70 | File Upload |  | Uploading File | Verifying upload file button or link is present. | "Upload File" button or link should be present. | Found as per expectation |  |  |  |  | Not Executed
Not Executed
71 |  |  |  | Verifying the upload button or link should be clickable. | "Upload File" button or link should be clickable. | Found as per expectation |  |  |  |  | Not Executed
72 |  |  |  | Verifying that the whole button including the button text should be clickable. | The entire button, including the text, should be clickable. | Found as per expectation |  |  |  |  | Not Executed
73 |  |  |  | Verifying an error message shown if the file size is large than the allowed one. | An error message should be displayed if the file size exceeds the allowed limit. | Found as per expectation |  |  |  |  | Not Executed
74 |  |  |  | Verifying an error message if the file is empty and has no content. | An error message should appear for an empty file. | Found as per expectation |  |  |  |  | Not Executed
75 |  |  |  | Drag and drop functionality should work properly for the allowed file types. | Drag and drop should work correctly for allowed file types. | Found as per expectation |  |  |  |  | Not Executed
76 | Filter Management |  | Search Functionality | Verifying the search field is present and aligned. | The search field should be present and properly aligned on the page. | Found as per expectations |  |  |  |  | Not Executed
77 |  |  |  | Verifying spelling and grammar should be correct for placeholder text. | The spelling and grammar of the placeholder text should be correct. | Found as per expectations |  |  |  |  | Not Executed
78 |  |  |  | Verifyinging an error message should display for blank input. | An error message should be displayed when the input is left blank. | Not found as per expectation |  |  |  |  | Not Executed
79 |  |  |  | Verifyinging pagination added in case the search result goes on the number of pages. | Pagination should be added when the search results exceed one page. | Not found as per expectation |  |  |  |  | Not Executed
80 |  |  |  | Checkinging if the user can paste the keyword with the mouse. | User should be able to paste the keyword using the mouse. | Found as per expectation |  |  |  |  | Not Executed
81 |  |  |  | Checkinging the search is working by adding keywords and on click on the search button. | Search should work when keywords are entered and the search button is clicked. | Not found as per expectation |  |  |  |  | Not Executed
82 |  |  |  | Verifying the search is working by adding keywords and pressing the Enter key on the keyboard. | Search should work when keywords are entered and the Enter key is pressed. | Not found as per expectation |  |  |  |  | Not Executed
Negative test
mmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnnbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbbmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmmm

## Test Summary Report
Test Case Report | [5 empty] | Result :
Project Name | Flight Expert
Module Name | User Account Management, Flight Booking, Hotel Booking, Visa Processing , eSIM Purchase |  |  |  |  | Total No. | Status | New Features:- | Testing Scope:-
Feature Name | Register Account ,Account Login,Transaction Functionality, Search Functionality
Test Case Version | 1 |  |  |  |  | 1 | PASS
Written By | Md Jahidul Islam |  |  |  |  | 0 | FAIL
Executed By | Md Jahidul Islam |  |  |  |  | 82 | Not Executed
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Testing Environment : Google Chrome Browser
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 1 | 0 | 82 | 0 | 83
Grand Total | 1 | 0 | 82 | 0 | 83
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Bug Report
Bug Reporting
#SL 01
Issue:
Reproducing Steps:
1. Go to the URL
2
Env:
Module:
Priority:
Severity:
Screenshot:
Expected:
Responsible QA: Md Jahidul Islam
#SL 02
Issue:
Reproducing Steps:
1. Go to the URL
2
Env:
Module:
Priority:
Severity:
Screenshot:
Expected:
Responsible QA: Md Jahidul Islam

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (82/82)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/82)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (66/82)*100 = 80.5%
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (16/82)*100 = 19.5%
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/82)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A